## Sheet1
ID	Name	Description	Priority	Effort	Status	Notes
1	Re-organize folder and app structure	Decide how to split up into apps. Folder structure and depth	Must	Low	Finished
2	Setup text editor	Setup good color scheme (Obisidian) so I'm more efficient with the editor.	Should	Low	Finished
3	Setup Linux Mint dev box	Linux Mint is newer and nicer feeling to debian. Is it worth switching to it for the rest of the project?	Could	Medium	Not Started
4	Performance of player generation	The Distribution class is slow in generating player attributes.	Could	Medium	Not Started
5	Position based talent profiles	Need to design talent profiles differently. Perhaps approximate known continuous distribution like log normal. Currently not realistic – positions like QB and DE produce more 5 star talent than others. However, with the exception of kickers there is a pretty good distribution of top talent by position. QB, RB, WR, DE, LB, CB are probably the primary positions.	Could	High	Not Started
6	URL layout and organization (rough)	Identify the main pages and views	Must	Medium	Not Started
7	Use PostgreSQL	SQLite is not suitable for multi user site.	Could	Medium	Finished
8	Choose better project name		Should	Low	Finished
9	Create new virtualenv for project		Must	Low	Finished
10	Remove django-tables2 app for now..	We will need a tables app later but it adds unnecessary complication for now	Should	Low	Finished
11	Research eclipse and other IDEs	Long term IDE might make work in django easier	Could	Medium	Not Started
12	Move design docs	Move the spec, data model and related docs to either local .ods format or github wiki	Could	Medium	Not Started
13	Import static player data (first names, positions,etc) in app	Currently the static data needed for player creation are loaded manually into the sqlite3 database file. It's better to load these records into the database at runtime (when needed) because then the whole database can be created from the input data files on the fly	Should	Medium	Completed	Created script to import the csv records. Note: Only works for sqlite3. When switching to PostgreSQL will need to load the data differently.
14	Use machine independent project path	PROJECT_PATH is currently hard coded	Must	Low	Not Started
15	Do csv model imports only once	Csv importing is slow and should only be done once, perhaps when the server starts?	Should	Medium	Abandoned
16	Finalize recruit pitch preferences	Research NCAA series and other sources to come up with the pitch preferences.	Must	High	Not Started
17	Design data model for player pitch preferences		Must	Medium	Not Started
18	Implement player pitch preference attribute generation	Generate pitch preferences similarly to how other player attributes are generated	Must	Medium	Not Started
19	Evalute frontend frameworks	Decide if front end framework, or CSS preproccessor, or pure html5 and css3 is the best approach	Should	High	Started
20	Try bootstrap	Try to get bootstrap to display the recruit classes in nice tables.	Must	Medium	Started
21	Use fixtures to import initial data		Must	Medium	Not Started
22	Design html templates for main pages	Need html templates for player rankings, school rankings, player detail, school detail with multiple views to filter data.	Must	Medium	Not Started
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100